## Cover Page
Local Child Poverty Action Report 2022/2023
Reporting Period 1st April 2022 - 31st March 2023

## Work
Work - Provide opportunities and support needed to enter, sustain and progress in work. (Real Living Wage gender employment and pay gaps and rurallity) | Responsible Services | RAG | Progress Update(Please quantify - provide information on numbers/ beneficiaries/outcomes)
We will increase the number of affordable homes let from PKC own stock | Housing |  | 203 affordable homes were delivered - of these, 130 were Social Rent, 49 Mid-Market Rent and 24 Low Cost Home Ownership. Affordable rent levels were maintained at 9% lower than neighbouring authorities and 23% lower than local housing associations. 300 people were assisted to move into their new homes thorugh our Property Ready and Prevention Funds and £50,000 was spent providing home starter and furniture packs.
We will increase opportunities for eligible families based on low incomes to access childcare across PKC. | ECS |  | Wraparound Care Service redesign in 2 settings, Pitlochry and Inchview to provide 8-6 service. Allowing parents to use childcare vouchers. Awaiting further SG funding and guidance.
We will ensure there are sufficient childcare places for 2 – 5 year olds across public/community/private provision to support parental employment and endeavour to do the same for 0-2 year olds as SG resources to support expansion become available. | ECS |  | 6394 childcare places were provided across the public and third sector
We will create an online resource that provides Parents and Carers with up to date and timely information to support their child or family. | ECS |  | This action will be progressed troughthe Education Parental Involement and Engagement Strategy launched in August 2023. Launched in year 2 session 24/25
We will liaise with funded providers to progress their commitment to paying the real Living Wage to staff delivering funded hours of ELC. | ECS- Early Learning and Childcare |  | In June 2023, as part of the contract management process for funded providers delivering ELC, all were asked to elaborate how they are committed to fair working practices for workers, including paying the real Living Wage. Of 34 funded provider ELC nursery settings, 24 advised that all staff are paid at least the real Living Wage, with a further three advising that more than half of staff on their payroll receive at least the real Living Wage. We continue to work closely with our funded providers to progress their commitment to the real Living Wage through ongoing discussion and focus group work. PKC also approved increases to the Sustainable Rate paid to funded providers in August 2022 and in April 2023 to support business sustainability and continued affordability for payment of the real Living Wage for ELC staff.
We will establish an in-work poverty task force | NHS Tayside |  | A Cost of Living Staff group has been established. It is co-chaired by a representative from the Directorate and Staff0-Side (trade Union). The group have developed new resources for staff including a Cost-of-Living Directory and provided awareness sessions delivered by external agencies on financial capability and energy advice.
NHS Tayside will become a fully accredited Living Wage employer | NHS Tayside |  | NHS Tayside and Perth and Kinross Council are fully accreited Living Wage employers
We will increase the uptake of eligible families accessing their Strong Start 2 place | ECS – early Learning and childcare |  | Uptake of Strong Start 2 places continues to increase, with 246 two -year olds accessing funded provision compared with 164 in the previous year. Figures include 49 children who were approved for funded sessions of ELC througho ur Support for Children and families referral process who would not otherwise have met set eligibility criteria. | o
We will secure more funding to increase financial support to community transport schemes | Communities – Business and Resources |  | awaiting infor M Roy
We will increase the number of demand responsive transport schemes in deep rural areas | Communities – Business and Resources |  | awaiting infor M Roy
We will run awareness campaigns to increase uptake of free travel passes by the under 22s | Communities – Business and Resources |  | awaiting infor M Roy
We will support 35 parents experiencing poverty whilst in employment and/or assist in moving into good quality, well paid sustainable employment | Skills and Employment Initiatives |  | 78 parents are being supported to find work; 30 who are currenlty in work are being supported to sustain employment or progress to better paid/more skilled employment.
We will support 17 parents experiencing poverty by funding training and development opportunities, utilising the Elev8 Training Grant | Skills and Employment Initiatives |  | 10 parents have received Elev8 training grants.
We will assist public and third sector employers to create 58 new labour market opportunities for long term unemployed people for a period of up to 26 weeks | Skills and Employment Initiatives |  | Delay of launch and funding requirements from SG proved difficult to attract interest 1st sign up Aug 2022 and latest start date Nov 2022. Of the 58 LTU opportunities allocated to PKC, 35 placements were accessed: 19 with PKC and 16 with external and ALEO's. of the 19 with PKC, 10 secured employment within the organisation, and 1 outwith , of these 6 are on permanent contracts with excellent benefits packages. 9 participants on external placements have secured continued employment in the organisation they were placed in. of the 35 placements 3 participants have gone into education.
We will assist in the creation of 120 new job opportunities, utilising PKC and Scottish Government funding | Skills and Employment Initiatives |  | 86 jobs have been created via Employer Recruitment Incentives (over the last 2 years)
We will develop a suite of skills academies to allow our residents to gain valuable accredited skills to aid progression in or into employment | Skills and Employment Initiatives |  | A pilot CodeClan Youth Academy supported 6 young people to develop coding and software development skills. Through the LEP Challenge Fund a new HGV/LGV training academy was established delivered by Nithcree Training. 50 particpants started the course,39 have passed their HGV licence and 36 are now in FT employment.

## Dignified Living
Dignified Living - Maximise support available to families to lead dignified lives and meet therie basic needs. (Rural poverty premium, gypsy travellers and other minority ethnic groups, stigma) | Responsible Services | RAG | Progress Update
A mobile phone app will be developed to enable access to information and advice on how to tackle fuel insecurity across Tayside | NHS Tayside |  | Warmth Matters app is still under development with a launch date planned for the end of May. It covers Fuel Help, Debt and Benefits, Cost of Living and Health. It is beign tested by a user panel set up by NHS Tayside's Patient Involvement Team and the TRIC
Share and promote the NHS National Services Scotland Community Benefit Gateway (CBG) to elp reduce health inequalities across Tayside. | NHS Tayside |  | NHS Tayside Community benefit Gateway has been established and includes colleagues from Public Health and Procurement and PKAVS. Sign ups to the CBG portal have increased with 64 new registrations from the third sector. NHS t ayside has the second highest number of open needs per Health Board in Scotland. 60 new suppliers have signed up with a total of 244 suppliers in the system.
Increase the number of health and educational income maximisation referrals to welfare/energy advice services across Tayside. | NHS Tayside |  | 279 referrals were made to Welfare Rights teams across Tatside with an average financial gain of £1175. In addition there were 412 referrals to Home enegry Scotland.
Cost of Living and Child Poverty training to be delivered to, and promoted with, Early Year practitioners across Tayside. | NHS Tayside |  | Poverty sensitive practice training is being revised and will be offered in a pilot session in October 2023. Training was provided to PKC's Early Learning and Childcare staff around access to benefits and debt advice, home energy support and the impact of poverty.
We will put social needs screening in place for all child concern reports which addresses the impact of poverty on those children and families for whom a concern has been reported | Child Protection Committee |  | A workshop on social needs screening is planned for Summer 2023.
We will ensure all frontline workers and service managers are aware of issues relating to poverty related stigma and dignity (Public Health Scotland Training Programme) | ALL |  | Public Health Scotland training programme is not yet available. A series of Cost-of-Living crisis and Poverty realted awareness sessions were held during Challenge Poverty Week in October 2022 and were open to all PKC employees.
We will continue to maximise streamlining of council concessions | Customer Services Board |  | Free School Meals and School Clothing Grant applications were streamlined in June 2022 with one application covering both concessions.
We will deploy Cash 1st approaches to reduce stigma and promote dignified entry points for help and support | Welfare Rights, ECS, Housing Services, HSCP, Third Sector |  | Acoordinated approach to the Cash-First Programme is being led by Perth CAB who have received funding from the Tressel Trust to employ a Cash-First Project Officer to take this project forward and ensure collaboration across the public and third sector. PKC distributed £3.2M in cash first payments. 926 tenants experiencing financial difficulty benefitted rom income maximisation delivered through the Financial Inclusion Project by Perth CAB. £950,00 has been provided to support 1725 tenants via the Tenancy Sustainment Fund since 2018 - this prevents homelessness and helped tenants cope with the Cost-of-Living crisis. Frontline staff were empowerd to respond quickly and effectively to support 167 tenants experiencing a financial crisis with Think Yes funding of £30,000.
We will deliver a Cost-of-Living Crisis public awareness campaign focussing on benefits maximisation, energy efficiency food and crisis support for struggling families | Communities/ Welfare Rights |  | A Cost-of-Living Crisis public awareness campaign was delivered with additional web-based information being provided and social media outlets used to promote information on where people could go to get help. The Community Planning Partnership provided an interactive map on where people could access warm spaces, warm home packs and community food offers.
We will deliver a Cost-of-Living Crisis Support programme aimed at mitigating the impact on struggling families | ALL |  | PKC provided £570,000 in additional funds -of this £420,000 was available for warm spaces, food and warm home packs. £170,000 was distributed to 95 community organisations and £250,000 was given to 85 community organisations for food/warm home packs. In total 120 organisations were funded, 16,575 people benefitted from the provision (11% of the population of Perth and Kinross) and 1049 volunteers were involved in delivering support to individuals and families. We expanded the range of energy advice services available to residents reaching 495 households with energy efficiency advice and measures to help reduce their heating bills.
We will offer All Families a welfare rights check | Welfare Rights |  | PKC's Welfare Rights Team recieved 7476 contacts and 3775 complex cases handled by the Welfare Rights Team. The Welfare Rights Team achieved client financial gain of £6.5M in social security benefits - an increase of 22% on the previous year. The Welfare Rights Team also administered the Council's Financial Insecurity Fund, recieveing 2,111 applications with a spend of £520k. In addition, the Scottish Welfare Fund Team recieved 6539 crisis grants with a spend of £574k, 8235 local low-income support payments with a spend of £997k, 1321 community care grants with a spend of £654k, 2790 discretionary housing payments with a spend of £994k, 719 self-isolation grants witha spend of £256k. The Local Taxes Team administered1029 Energy Bill Support Payments, 44,299 cost-of -iving payments paid to council tax accounts and 662 cost-of-living payments were paid direct to bank accounts
We will develop a test of change project in 3 localities to deliver tailored support packages to Priority Families | ALL |  | Locality based approaches to supporting children and families affected by poverty are being developed in Crieff, Letham, Coupar Angus and Highland Perthshire. Highland Perthsire MDT is being supported by the Improvement Service to develop and implement a locality based Child Poverty action Plan which includes a scaleable support and connect programme. The CPP commissioned Iconic Consulting to work with the community to develop a new Town Centre Action Plan to address priority issues including poverty, health and wellbeing. A data discovery project has been commissioned to identify localities where there is the greatest unmet need amongst families affected by poverty.
We will offer welfare rights advice to all Perth and Kinross employees | Welfare Rights |  | Welfare Rights advice is offered to all PKC employees via their electronic pay slip every month. There is information on the Council's intranet, within the Employee Benefits section of the intranet and within HR templates signposting employees to the Council's Welfare Rights Team.
We will work with cross sectoral partners to provide food, childcare and activities during holiday periods to eligible families based on low income. | ECS |  | PKC was allocated £242m363 for summer food/activities, this was augmented by £154,000 from the PKC budget. Funding was awarded to 45 community groups to deliver "Fuelled for Fun2 programmes. 4796 children registered at services and 4492 attended summer play and food sessions. 30,042 snacks and meals were provided to children and families across PKC. An average of 1000 meals a day were provided.
We will progress the forthcoming Scottish Delivery Plan detailing the provision of wraparound childcare, offering childcare before and after school and during school holidays | ECS |  | Kids Clubs supported 43 free ch ildcare places with lunch and snacks over holidya periods. The Childcare Strategy team supported 253 children during holiday periods. The Parent and Family Learning team supported 279 families during the holiday periods. An additional 271 families and 562 children received a Christmas food and activity hamper.
We will increase the take-up of free school meals | ECS |  | Baseline figures for the uptake of free school meals are now available - showing 65% for PrimarySchools and 45% for Secondary Schools. 7,700 meals are provided each day, action splans are in place to improve all areas of meal uptake.

## Survive and Thrive
Survive and Thrive - Supporting the next geenration to survive and thrive (Close attainment gap, disabled young people into higher education and jobs market, mental health and wellbeing) | Responsible Services |  | RAG | Progress Update
We will establish an Anti- Poverty Task Force to provide leadership and co-ordination around poverty related matters CPWG | CPWG |  |  | The Anti-Povety Task Force has been established with members from across public, private and third sectors. It has co-ordinated our Cash-First approach, facilaited expansion of the Perth Gift Card to supermarkets, enabled the business sector to link with the NFU to lead discussions on farmers supplying fresh produce which will be turned into meals, and has several intiatives at the early planning stage e.g. community minibus trial in Letham.
We will establish a website to provide one stop shop for parental advice encompassing mental health and wellbeing | ECS | TRIC |  | This action is being progressed via the Whole Family Health and Wellbeing Programme.
We will increase support available to children and young people experiencing wellbeing challenges | ECS |  |  | A further 18 schools were recruited to the Nurturing Relationships Whole School Programme. 8 Primary Schools and 2 Secondary Schools have implemented phase 2 of the Nurturing Relationships Programme. The majority of ELC settings have appointed an ELC Wellbeing Champtionship, and additional training enables staff to improve support for children's emotional development. The Health adn Wellbeing Census identified mental health, substance use, relationships and sexual health, bullying and food poverty as priorities. Further analysis is required to develop an understanding of the variations in data arising from poverty.
We will raise attainment and achievement for all and close the attainment gap through our Raising Attainment Strategy | ECS | ECS |  | The poverty-related attainment gap shows amixed picture, narrowing for P4 and S3, but some areas widening at P1 and P7 and remaining largely static for school leavers. The quality and extent of individual Pupil Equity Fund spend has improved with 90% of the fund spent within planned timescales. The Closing the Gap toolis helping to evidence the impact of interventions being utilised to improve attainment in schools.
Work with partners to support recovery, through implementation of evidence-based approaches to target literacy, numeracy and health and wellbeing outcomes. | ECS | ECS |  | The Literacy and Numeracy Strategies have been reviewed to create frameworks to raise attainment based on current attainment data. These outline PKC expectations, recommendations and appraoches to the delivery of literacy andnumeracy from 2 - 18 and are supported by a professional learning programme for school staff.
Work with partners to support implementation of the Community Mental Health fund. | ECS | ECS |  | 258 children accessed support or services funded via the CMHP between July and December 2022. There are 30 projects in progress or being developed via the programme. Funding also enabled The Lighthouse for Perth to offer support for families of young people at risk of suicide or self-injury.
Extend Free School meal provision to all Primary pupils pending additional SG support. | ECS | ECS |  | Awaiting confirmation of additional Scottish Government funding before implementation.